## Sheet1
Sl No	Tasks	Status
1	For each iteration create new folder ‘Iteration_n’	Done
2	Including functions in the controlDict file of NS for the creation of force.dat file for calculating the drag force	Done
3	Creation of solver for optimisation and validation	Done
4	Copy folders ‘NS’ and ‘OS’ from ‘Reference’ folder into the ‘Iteration_n’ folder	Done
5	Update blockMeshdict file in ‘Iteration_n/NS/system/’ folder with updated coordinates for the following points: 1,2,7,9,11,4,5,6,8,10 & 20, 21, 26, 28, 30, 23, 24, 25, 27, 29	Done
6	Update blockMeshdict file in ‘Iteration_n/NS/system/’ folder with updated intermediate points for all the splines	Done
7	Running ‘blockMesh’, ‘checkMesh’, ‘pisoFoam’	Done
8	Copy files ‘p’ and ‘U’ from the last time step of ‘NS’ folder to the ‘OS/0/’ folder	Done
9	Calculation of drag force ‘D’ from ‘NS/postProcessing/forces/0/forces.dat’ file	Done
10	Updation of boundary condition of ‘OS/0/Uadj’ file with the calculated ‘D’ value	Done
11	Copy and paste ‘NS/system/blockMeshdict’ to ‘OS/system/’ folder	Done
12	Running ‘blockMesh’, ‘checkMesh’, ‘pisomosiFoam’	Done
13	Read ‘OS/BoundaryResults.txt’ file to read the coordinates, U , Uadj, pAdj, gradU, gradUadj and facenormal values	Done
14	Calculate ‘s’ for each point	Done
15	Formulate the final correction equation to update the vector of coordinates	Done
16	Calculate the coordinates of the below points: 1,2,7,9,11,4,5,6,8,10 & 20, 21, 26, 28, 30, 23, 24, 25, 27, 29	Done
17	Calculate the coordinates of the intermediate points of the splines	Done
18	Ensuring the volume is constant in each iteration	Done
19	Control sudden jump of coordinates during the updation of coordinates	Done
20	Control the mesh size if required for controlling the courant no	Not Done
21	Write a DragForce.dat file with drag forces calculated in each iteration	Done
22	Controlling the block shape based on change in sub boundary shape	Done
23	Run Simulation with circle of a radius other than 0.5	Not Done	Jishnu
24	Make the code flexible cleaning up hard coded snippets	Not Done
25	Run Simulation with a hexagon of same volume as that of circle of radius 0.5	Not Done	Aju
23	Run Simulation with circle of a radius 0.5 but with different Re	Not Done	Prabhu